## login and register
User Category | Module | URL | Response | Keyvalues | Task list | Task Start Date | Targeted End Date | Task End Date | Remarks
Admin | Login | http://kaizenat.com/LUPA/admin/login | status_response, success = 1 (Sucessfully logging in) , success=0 (Errors will be displayed like email does not exist or password is incorrect) | email,password | UI : Completed Integration : Completed | 18/12/2018 | 19/12/2018 | 19/12/2018 | 19/12/2018 : API integration is completed.Test case: nageshwararao1996@gmail.com , password:123456
| Forgot Password | http://kaizenat.com/LUPA/admin/forgot/password | status_response , success = 1 (OTP successfully sent) success=0 (Errors will be displayed like email does not exist or password is incorrect) | email | UI : Completed Integration : Completed | 21/12/2018 | 23/12/2018 | 22/12/2018
| Forgot Password OTP Page | http://kaizenat.com/LUPA/admin/password/forgotpassword/otp | status_response , success=1, (Please reset your new password) success = 0 (Invalid OTP, please enter correct otp) | otp | UI : Completed Integration : Completd | 21/12/2018 | 23/12/2018 | 22/12/2018
| Password Reset Page | http://kaizenat.com/LUPA/admin/password/reset | status_response,success= 1(Sucessfully logging in takes to dashboard.),success=0 (Password do not match or email does not exist) | email, password, password_confirmation | UI : Completed Integration : Completed | 21/12/2018 | 23/12/2018 | 22/12/2018
| Setting |  |  |  | UI : Completed Integration : Completed | 2018-12-22 | 24/12/2018 | 2018-12-23
| Profile |  |  |  | UI : Completed Integration : Completed | 2018-12-23 | 24/12/2018 | 24/12/208
| Cost calculator |  |  |  | UI : Completed Integration : Completed | 2018-12-26 | 25/12/2018 | 2018-12-26
| SMTP |  |  |  | UI : Completed Integration : Completed | 2018-12-27 | 26/12/2018 | 2018-12-27
| Dashboard |  |  |  | UI : In progress Integration : In progress |  | 2019-01-03
| Favourites |  |  |  | UI : In progress Integration : Yet to start |  | 2019-01-03
| Product wise Dashboard |  |  |  | UI : In progress Integration : Yet to start |  | 2019-01-03
| Report license dashboard |  |  |  | Yearly UI : in progreess Integration : Pending Monthly : UI : Yet to start Integration : Yet to start Weekly : UI : yet to start Integation : yet to start Last 5 minutes : UI : yet to start Integration : yet to start |  | 2019-01-03 |  | 19/12/2018 :Weekly and last 5 minutes design section is missing in pdf
Department Manager | Register Page | http://kaizenat.com/LUPA/departmentmanager/register | status_response , success= 1(Sucessfully takes to otp page ) success = 1 (Validation Errors) | name,email,phone,department, password | UI : Completed Integration : Completed | 2018-12-23 | 25/12/2018 | 25/12/2018
| Register confirmation OTP page | http://kaizenat.com/LUPA/departmentmanager/otp | status_response, success = 1 (if successful, gives success message and takes to login page where they have to login again. ) , success=0 (Validation Error messages ) | otp | UI : Completed Integration : Completed | 2018-12-23 | 25/12/2018 | 25/12/2018
| Login Page | http://kaizenat.com/LUPA/departmentmanager/login | status_response, success = 1 (Successfully Logging in taking to dashboard) , success=0 (Validation Error messages ) | email, password | UI : Completed Integration : Completed | 2018-12-23 | 25/12/2018 | 25/12/2018
| Forgot password | http://kaizenat.com/LUPA/departmentmanager/password/forgotpassword/otp | status_response, success=1 (OTP successfully sent) , success=0 ( validation error ) | email | UI : Completed Integration : Completed | 2018-12-23 | 25/12/2018 | 25/12/2018
| Reset password | http://kaizenat.com/LUPA/departmentmanager/password/reset | status_message , success=1 (successfully logging in), success=0 (validation errors) | email, password, password_confirmation | UI : Completed Integration : Completed | 2018-12-23 | 25/12/2018 | 25/12/2018
| Dyna compares |  |  |  | UI : Yet to start Integration : Yet to start |  | 2019-01-04 |  | 29/12/2018: The requirement is not clear and the APIs are pending.
| Dashboard |  |  |  | UI : Yet to start Integration : Yet to start |  | 2019-01-08
| Faourite |  |  |  | UI : Yet to start Integration : Yet to start |  | 2019-01-08
| Notification |  |  |  | UI : Yet to start Integration : Yet to start |  | 2019-01-10
| Product wise Dashboard |  |  |  | UI : In progress Integration : Yet to start | 2018-12-28 | 2019-01-08
| Report license dashboard |  |  |  | Yearly UI : in progreess Integration : Pending Monthly : UI : Yet to start Integration : Yet to start Weekly : UI : yet to start Integation : yet to start Last 5 minutes : UI : yet to start Integration : yet to start |  | 2019-01-08 |  | 19/12/2018 :Weekly and last 5 minutes design section is missing in pdf
| Setting |  |  |  | UI : Completed Integration : In Progress |  | 2018-12-29
| Profile |  |  |  | UI : Completed Integration : Completed | 2018-12-25 | 2018-12-28 | 2018-12-26
User | Register page otp | http://kaizenat.com/LUPA/user/otp | status_response , success= 1(Sucessfully takes login page where he has to login again. ) success = 1 (Validation Errors) | otp | UI : Completed Integration : Completed | 17/12/2018 | 22/12/2018 | 21/12/2018
| login page | http://kaizenat.com/LUPA/user/login | status_response, success = 1 (Successfully Logging in taking to dashboard) , success=0 (Validation Error messages ) | email, password | UI : Completed Integration : Completed | 17/12/2018 | 22/12/2018 | 21/12/2018 | 19/12/2018: API integration is completed. Test case: user@kaizenat.com , password:123456
| forgot password | http://kaizenat.com/LUPA/user/password/reset | status_response , success = 1 (OTP successfully sent) success=0 (Errors will be displayed like email does not exist or password is incorrect) | email | UI : Completed Integration : Completed | 17/12/2018 | 22/12/2018 | 21/12/2018
| forgot password otp page | http://kaizenat.com/LUPA/user/password/forgotpassword/otp | status_response , success=1, (Please reset your new password) success = 0 (Invalid OTP, please enter correct otp) | otp | UI : Completed Integration : Completed | 17/12/2018 | 22/12/2018 | 21/12/2018
| Password Reset Page | http://kaizenat.com/LUPA/user/password/forgotpassword/otp | status_response,success= 1(Sucessfully logging in takes to dashboard.),success=0 (Password do not match or email does not exist) | email, password, password_confirmation | UI : Completed Integration : Completed | 17/12/2018 | 22/12/2018 | 21/12/2018
| Dashboard |  |  |  | UI : In progress Integration : Yet to start | 21/12/2018 | 30/12/2018
| Faourite |  |  |  | UI : In progress Integration : Yet to start |  | 30/12/2018
| Product wise Dashboard |  |  |  | UI : In progress Integration : Yet to start | 2018-12-28 | 30/12/2018
| Report license dashboard |  |  |  | Yearly UI : in progreess Integration : Pending Monthly : UI : Yet to start Integration : Yet to start Weekly : UI : yet to start Integation : yet to start Last 5 minutes : UI : yet to start Integration : yet to start |  | 30/12/2018 |  | 19/12/2018 : Weekly and last 5 minutes design section is missing in pdf
| Profile |  |  |  | UI : Completed Integration : Completed | 2018-12-26 | 28/12/2018 | 2018-12-26

## API lists
User Category | Module | URL | Method | Response | Keyvalues |  | Status
Admin | Login | http://kaizenat.com/LUPA/admin/login | POST | "status_respond": "{\"message\":\"The email field is required.\",\"Success\":0}", "status_respond": "{\"message\":\"The password field is required.\",\"Success\":0}"}, "status_respond": "{\"success\":0,\"message\":\"Username or Password is incorrect\"}", "status_respond": "{\"success\":1,\"message\":\"Successfully logged in.\"}" | email,password
| Forgot Password | http://kaizenat.com/LUPA/admin/password/email | POST | "status_response": "{\"message\":\"The email field is required.\",\"Success\":0}" , "status_response": "{\"message\":\"The selected email is invalid.\",\"Success\":0}", "status_respond": "{\"success\":1,\"message\":\"OTP successfully sent\"}", | email
| Forgot Password OTP Page | http://kaizenat.com/LUPA/admin/password/forgotpassword/otp | POST | "status_response": "{\"message\":\"The otp field is required.\",\"Success\":0}", "status_response": "{\"success\":0,\"message\":\"Invalid OTP, please enter correct otp\"}", "status_response": "{\"success\":1,\"message\":\"Please reset your new password\"}", | otp
| Password Reset Page | http://kaizenat.com/LUPA/admin/password/reset | POST | "status_response": "{\"data\":\"The email field is required.\",\"Success\":0}", "status_response": "{\"data\":\"The password field is required.\",\"Success\":0}", "status_response": "{\"data\":\"The password confirmation does not match.\",\"Success\":0}", "status_response": "{\"message\":\"Login successfull, taking to dashboard\",\"Success\":1}" | email, password, password_confirmation
| SMTP existing data | http://kaizenat.com/LUPA/admin/smtp_existing_details | GET | "status_response": "{\"success\":1,\"message\":\"Successfully retrived\",\"data\":{\"mail_driver\":\"smtp\",\"host\":\"smtp.office365.com\",\"port\":\"587\",\"email\":\"android@kaizenat.com\",\"password\":\"Sreedinu@123\",\"encryption_type\":\"tls\"}}" |  | Note: select port in dropdown(25,465,587), encryption type(ssl, tls,not secure)
| updating form | http://kaizenat.com/LUPA/admin/smtp_update | POST | "status_response": "{\"success\":0,\"message\":\"The mail driver field is required.\"}", "status_response": "{\"success\":1,\"message\":\"SMTP details successfully updated\"}" | mail_driver, host, port, email, password, encryption_type
| Email Testing whether working or not | http://kaizenat.com/LUPA/admin/test_mail | POST | "status_response": "{\"success\":0,\"message\":\"The email field is required.\"}", "status_response": "{\"success\":\"0\",\"message\":\"Test mail failed \"}", "status_response": "{\"success\":\"1\",\"message\":\"Mail successfully sent \"}" | email
Cost calculations APIS
| inserting purchase details form | http://kaizenat.com/LUPA/admin/cost_calculation | POST | "status_response": "{\"message\":\"The software name field is required.\",\"Success\":0}", "status_response": "{\"message\":\"Successfully added\",\"Success\":1}", "status_response": "{\"message\":\"Please add the DYNA purchase cost first.\",\"Success\":0}" | software_name, year_of_purchase, license_type, lease_months(when they select lease license only), licenses_purchased, purchase_cost
| listing purchase details | http://kaizenat.com/LUPA/admin/purchase_list | GET | "success": 1, "data": [ {}
| delete purchase | http://kaizenat.com/LUPA/admin/delete_purchase?id=402 | GET | "status_response": "{\"message\":\"The purchase id field is required.\",\"Success\":0}", "status_response": "{\"message\":\"The selected id is invalid.\",\"Success\":0}",http://kaizenat.com/LUPA/admin/delete_purchase | id
Settings page Apis
| Total departments List | http://kaizenat.com/LUPA/admin/totaldepartments_list | GET | "status_response": "{\"message\":\"Successfully retrieved\",\"Success\":1,\"data\":[{\"id\":5,\"department_name\":\"CRASH\"},{\"id\":6,\"department_name\":\"NVHH\"}]}"
| Total Licenses list used & remaining | http://kaizenat.com/LUPA/admin/total_license | GET | "status_response": "{\"message\":\"Successfully retrieved\",\"success\":1,\"data\":[{\"product_name\":\"LSDYNA\",\"total_license\":10,\"license_remaining\":5},{\"product_name\":\"MSC\",\"total_license\":20,\"license_remaining\":10},{\"product_name\":\"ALTAIR\",\"total_license\":30,\"license_remaining\":15},{\"product_name\":\"BETA CAE\",\"total_license\":40,\"license_remaining\":20}]}"
| adding department | http://kaizenat.com/LUPA/admin/deptAdd | POST | "status_response": "{\"message\":\"The department field is required.\",\"Success\":0}", "status_response": "{\"message\":\"Department addedd successfully\",\"Success\":1}" | department
| delete department | http://kaizenat.com/LUPA/admin/deptDestroy?id=5 | GET | "status_response": "{\"message\":\"Department successfully deleted.\",\"Success\":1}" | id
| department managers list | http://kaizenat.com/LUPA/admin/departmentmangers_list | GET | "status_response": "{\"message\":\"Successfully ,"status_response": "{\"message\":\"No data Found\",\"Success\":0,\"data\":[]}",retrieved\",\"Success\":1,\"data\":[{\"id\":1,\"name\":\"Nagesh\",\"email\":\"departmentmanagers@kaizenat.com\",\"department\":\"CRASH\",\"verified\":1,\"admin_approved\":0},{\"id\":6,\"name\":\"department managers\",\"email\":\"android@kaizenat.com\",\"department\":\"NVHH\",\"verified\":1,\"admin_approved\":1}]}"
| approving department manager | http://kaizenat.com/LUPA/admin/deptmanagerctivate?id=1 | GET | "status_response": "{\"message\":\"Department manager activated\",\"Success\":1}" | id
| block department manager | http://kaizenat.com/LUPA/admin/deptmanagerdeactivate?id=1 | GET | "status_response": "{\"message\":\"Department manager deactivated successfully\",\"Success\":1}" | id
| delete department manager | http://kaizenat.com/LUPA/admin/deptmanagerdelete?id=4 | GET | "status_response": "{\"message\":\"The selected id is invalid.\",\"Success\":0}", "status_response": "{\"message\":\"Department manager successfully deleted.\",\"Success\":1}" | id
| Users List | http://kaizenat.com/LUPA/admin/users_list | GET | "status_response": "{\"message\":\"Successfully retrieved\",\"Success\":1,\"data\":[{\"id\":4,\"name\":\"Nagesh\",\"email\":\"android@Kaizenat.com\",\"department\":\"CRASH\"},{\"id\":5,\"name\":\"User2\",\"email\":\"user2@kaizenat.com\",\"department\":\"CRASH\"},{\"id\":6,\"name\":\"user3\",\"email\":\"user3@kaizenat.com\",\"department\":\"NVHH\"}]}"
| block user | http://kaizenat.com/LUPA/admin/userblock?id=3 | GET | "status_response": "{\"message\":\"The selected id is invalid.\",\"Success\":0}","status_response": "{\"message\":\"User successfully blocked\",\"Success\":0}" | id
| unblock user | http://kaizenat.com/LUPA/admin/userunblock?id=3 | GET | "status_response": "{\"message\":\"The selected id is invalid.\",\"Success\":0}", "status_response": "{\"message\":\"User successfully Activated\",\"Success\":1}" | id
| delete user | http://kaizenat.com/LUPA/admin/userdelete?id=3 | GET | "status_response": "{\"message\":\"User successfully deleted.\",\"Success\":1}" | id
| transfer user | http://kaizenat.com/LUPA/admin/usertransfer | POST | "status_response": "{\"message\":\"Transfer request has been sent. User will remain in Existing department until transferred.\",\"Success\":1}" | todepartment, useremail,fromdepartment,username
| departments list (for user transfer purpose, only these should be displayed for when tried to select the user) | http://kaizenat.com/LUPA/admin/departments_list | GET | "status_response": "{\"message\":\"Successfully retrieved\",\"data\":[{\"department\":\"CRASH\"},{\"department\":\"NVHH\"}],\"Success\":1}"
profile setting APIs
| profile existing data | http://kaizenat.com/LUPA/admin/profile_existing_data | GET | "status_response": "{\"message\":\"Successfully retrieved\",\"Success\":1,\"data\":[{\"id\":1,\"name\":\"nag\",\"email\":\"admin@kaizenat.com\"}]}"
| profile update | http://kaizenat.com/LUPA/admin/profileupdate | POST | "status_response": "{\"message\":\"Profile successfully updated\",\"Success\":1}" | name, email, password, password_confirmation, id
Department Manager | Register Page | http://kaizenat.com/LUPA/departmentmanager/register | POST | "status_response": "{\"message\":\"The name field is required.\",\"Success\":0}", "status_response": "{\"message\":\"The department field is required.\",\"Success\":0}", "status_response": "{\"message\":\"The phone has already been taken.\",\"Success\":0}", "status_response": "{\"success\":1,\"message\":\"OTP successfully sent.\"}" | name,email,department, password
| Register confirmation OTP page | http://kaizenat.com/LUPA/departmentmanager/otp | POST | "status_response": "{\"message\":\"The otp field is required.\",\"Success\":0}", "status_response": "{\"success\":0,\"message\":\"Invalid OTP, Please enter correct OTP\"}", "status_response": "{\"success\":1,\"message\":\"Account Successfully Activated, and pending for admin approval\"}", | otp
| Login Page | http://kaizenat.com/LUPA/departmentmanager/login | POST | "status_response": "{\"success\":0,\"message\":\"The email field is required.\"}", "status_response": "{\"success\":0,\"message\":\"The password field is required.\"}", "status_response": "{\"success\":0,\"message\":\"Account Either password is incorrect or not activated or not approved by Admin\"}", "status_response": "{\"success\":1,\"message\":\"Successfully loggin in. taking to dashboard\"}" | email, password
| Forgot Password | http://kaizenat.com/LUPA/departmentmanager/password/email |  | "status_respond": "{\"success\":0,\"message\":\"The selected email is invalid.\"}", "status_respond": "{\"success\":1,\"message\":\"OTP successfully sent\"}" | email
| Forgot Password OTP Page | http://kaizenat.com/LUPA/departmentmanager/password/forgotpassword/otp | POST | "status_response": "{\"message\":\"The otp field is required.\",\"Success\":0}", "status_response": "{\"success\":1,\"message\":\"Success, Please reset your password\"}", | otp
| Reset password | http://kaizenat.com/LUPA/departmentmanager/password/reset | POST | "status_response": "{\"success\":0,\"message\":\"The email field is required.\"}", "status_response": "{\"success\":1,\"message\":\"Successfully logging in. taking to dashboard\"}", | email, password, password_confirmation
| profile existing data | http://kaizenat.com/LUPA/departmentmanager/profile_existing_data?id=6 |  | "status_response": "{\"message\":\"Successfully retrieved sd\",\"Success\":1,\"data\":{\"1\":{\"id\":6,\"email\":\"android@kaizenat.com\",\"name\":\"department managers\"}}}" | id
| profile update | http://kaizenat.com/LUPA/departmentmanager/profile | POST | "status_response": "{\"message\":\"Profile successfully updated\",\"Success\":1}" | id, name, email, password, cpassword
| Users List under his department | http://kaizenat.com/LUPA/departmentmanager/users_list?department=CRASH | POST | "status_response": "{\"message\":\"Successfully retrieved\",\"Success\":1,\"data\":[{\"id\":4,\"name\":\"Nagesh\",\"email\":\"android@Kaizenat.com\",\"department\":\"CRASH\",\"verified\":0},{\"id\":5,\"name\":\"User2\",\"email\":\"user2@kaizenat.com\",\"department\":\"CRASH\",\"verified\":1}]}" | department
| block user | http://kaizenat.com/LUPA/departmentmanager/userblock?id=1 | GET | "status_response": "{\"message\":\"User successfully blocked.\",\"Success\":1}" | id
| un block user | http://kaizenat.com/LUPA/departmentmanager/userunblock?id=1 | GET | "status_response": "{\"message\":\"User successfully Activated\",\"Success\":0}" | id
| delete user | http://kaizenat.com/LUPA/departmentmanager/delete_user?id=1 |  | "status_response": "{\"message\":\"User successfully deleted.\",\"Success\":1}" | id
| user transfer | http://kaizenat.com/LUPA/departmentmanager/usertransfer | POST | "status_response": "{\"message\":\"Transfer request has been sent. User will remain in Existing department until transferred.\",\"Success\":1}" | todepartment, useremail,fromdepartment,username
User | Register page | http://kaizenat.com/LUPA/user/register | POST | "status_response": "{\"message\":\"The phone has already been taken.\",\"Success\":0}", "status_response": "{\"success\":1,\"message\":\"OTP successfully sent.\"}", | name, email, department, password, password_confirmation
| Register page otp | http://kaizenat.com/LUPA/user/otp | POST | "status_response": "{\"success\":1,\"data\":\"Account Successfully Activated, Please Login again\"}", | otp
| login page | http://kaizenat.com/LUPA/user/login | POST | "status_response": "{\"success\":1,\"message\":\"Successfully logging in.\"}", "status_response": "{\"success\":0,\"message\":\"The password field is required.\"}", "status_response": "{\"success\":0,\"message\":\"The email field is required.\"}" | email, password
| forgot password | http://kaizenat.com/LUPA/user/password/email | POST | "status_respond": "{\"success\":0,\"message\":\"The email field is required.\"}", "status_respond": "{\"success\":1,\"message\":\"OTP successfully sent\"}" | email
| forgot password otp page | http://kaizenat.com/LUPA/user/password/forgotpassword/otp | POST | "status_response": "{\"message\":\"The otp field is required.\",\"Success\":0}", "status_response": "{\"success\":0,\"message\":\"Invalid OTP, Please enter correct OTP\"}", "status_response": "{\"success\":1,\"message\":\"Success, Please reset your password\"}" | otp
| Password Reset Page | http://kaizenat.com/LUPA/user/password/reset | POST | "status_respond": "{\"success\":1,\"message\":\"Successfully logging in.\"}", | email, password, password_confirmation
| profile_existing_data | http://kaizenat.com/LUPA/user/profile_existing_data?id=4 | GET | "status_response": "{\"message\":\"Successfully retrieved\",\"Success\":1,\"data\":[{\"id\":4,\"email\":\"android@Kaizenat.com\"}]}" | id
| profile update | http://kaizenat.com/LUPA/user/profile | POST | "status_response": "{\"message\":\"Profile successfully updated\",\"Success\":0}" | email, ncpassword, npassword, id
In Progress
Completed
Not Yet started

## product
user | Module | URL | Method | UI | Functionality
user | Product
settting page
Cost calculations
Dyna Compare
SMTP
admin
manager

## clarification
User | Module | URL | Method | clarification
| Dashboard | http://kaizenat.com/LUPA/dashboard | GET | Provide api for attached image. Refer screenshot-1

## screenshot
Screenshot - 1