## login and register
User Category | Module | URL | Response | Keyvalues | Task list | Task Start Date | Targeted End Date | Task End Date | Remarks
Admin | Login | http://kaizenat.com/LUPA/admin/login | status_response, success = 1 (Sucessfully logging in) , success=0 (Errors will be displayed like email does not exist or password is incorrect) | email,password | UI : Completed Integration : Completed | 18/12/2018 | 19/12/2018 | 19/12/2018 | 19/12/2018 : API integration is completed.Test case: nageshwararao1996@gmail.com , password:123456
| Forgot Password | http://kaizenat.com/LUPA/admin/forgot/password | status_response , success = 1 (OTP successfully sent) success=0 (Errors will be displayed like email does not exist or password is incorrect) | email | UI : Completed Integration : Completed | 21/12/2018 | 23/12/2018 | 22/12/2018
| Forgot Password OTP Page | http://kaizenat.com/LUPA/admin/password/forgotpassword/otp | status_response , success=1, (Please reset your new password) success = 0 (Invalid OTP, please enter correct otp) | otp | UI : Completed Integration : Completd | 21/12/2018 | 23/12/2018 | 22/12/2018
| Password Reset Page | http://kaizenat.com/LUPA/admin/password/reset | status_response,success= 1(Sucessfully logging in takes to dashboard.),success=0 (Password do not match or email does not exist) | email, password, password_confirmation | UI : Completed Integration : Completed | 21/12/2018 | 23/12/2018 | 22/12/2018
| Setting |  |  |  | UI : Completed Integration : Completed | 2018-12-22 | 24/12/2018 | 2018-12-23
| Profile |  |  |  | UI : Completed Integration : Completed | 2018-12-23 | 24/12/2018 | 24/12/208
| Cost calculator |  |  |  | UI : Completed Integration : In Progress |  | 25/12/2018
| SMTP |  |  |  | UI : Completed Integration : In Progress |  | 26/12/2018
| Dashboard |  |  |  | UI : In progress Integration : In progress |  | 2019-01-03
| Favourites |  |  |  | UI : In progress Integration : Yet to start |  | 2019-01-03
| Product wise Dashboard |  |  |  | UI : In progress Integration : Yet to start |  | 2019-01-03
| Report license dashboard |  |  |  | Yearly UI : in progreess Integration : Pending Monthly : UI : Yet to start Integration : Yet to start Weekly : UI : yet to start Integation : yet to start Last 5 minutes : UI : yet to start Integration : yet to start |  | 2019-01-03 |  | 19/12/2018 :Weekly and last 5 minutes design section is missing in pdf
Department Manager | Register Page | http://kaizenat.com/LUPA/departmentmanager/register | status_response , success= 1(Sucessfully takes to otp page ) success = 1 (Validation Errors) | name,email,phone,department, password | UI : Completed Integration : Completed | 2018-12-23 | 25/12/2018 | 25/12/2018
| Register confirmation OTP page | http://kaizenat.com/LUPA/departmentmanager/otp | status_response, success = 1 (if successful, gives success message and takes to login page where they have to login again. ) , success=0 (Validation Error messages ) | otp | UI : Completed Integration : Completed | 2018-12-23 | 25/12/2018 | 25/12/2018
| Login Page | http://kaizenat.com/LUPA/departmentmanager/login | status_response, success = 1 (Successfully Logging in taking to dashboard) , success=0 (Validation Error messages ) | email, password | UI : Completed Integration : Completed | 2018-12-23 | 25/12/2018 | 25/12/2018
| Forgot password | http://kaizenat.com/LUPA/departmentmanager/password/forgotpassword/otp | status_response, success=1 (OTP successfully sent) , success=0 ( validation error ) | email | UI : Completed Integration : Completed | 2018-12-23 | 25/12/2018 | 25/12/2018
| Reset password | http://kaizenat.com/LUPA/departmentmanager/password/reset | status_message , success=1 (successfully logging in), success=0 (validation errors) | email, password, password_confirmation | UI : Completed Integration : Completed | 2018-12-23 | 25/12/2018 | 25/12/2018
| Dyna compares |  |  |  | UI : Yet to start Integration : Yet to start |  | 2019-01-04
| Dashboard |  |  |  | UI : Yet to start Integration : Yet to start |  | 2019-01-08
| Faourite |  |  |  | UI : Yet to start Integration : Yet to start |  | 2019-01-08
| Notification |  |  |  | UI : Yet to start Integration : Yet to start |  | 2019-01-10
| Product wise Dashboard |  |  |  | UI : Yet to start Integration : Yet to start |  | 2019-01-08
| Report license dashboard |  |  |  | Yearly UI : in progreess Integration : Pending Monthly : UI : Yet to start Integration : Yet to start Weekly : UI : yet to start Integation : yet to start Last 5 minutes : UI : yet to start Integration : yet to start |  | 2019-01-08 |  | 19/12/2018 :Weekly and last 5 minutes design section is missing in pdf
| Setting |  |  |  | UI : Completed Integration : In Progress |  | 2018-12-29
| Profile |  |  |  | UI : Completed Integration : Completed | 2018-12-25 | 2018-12-28 | 2018-12-26
User | Register page otp | http://kaizenat.com/LUPA/user/otp | status_response , success= 1(Sucessfully takes login page where he has to login again. ) success = 1 (Validation Errors) | otp | UI : Completed Integration : Completed | 17/12/2018 | 22/12/2018 | 21/12/2018
| login page | http://kaizenat.com/LUPA/user/login | status_response, success = 1 (Successfully Logging in taking to dashboard) , success=0 (Validation Error messages ) | email, password | UI : Completed Integration : Completed | 17/12/2018 | 22/12/2018 | 21/12/2018 | 19/12/2018: API integration is completed. Test case: user@kaizenat.com , password:123456
| forgot password | http://kaizenat.com/LUPA/user/password/reset | status_response , success = 1 (OTP successfully sent) success=0 (Errors will be displayed like email does not exist or password is incorrect) | email | UI : Completed Integration : Completed | 17/12/2018 | 22/12/2018 | 21/12/2018
| forgot password otp page | http://kaizenat.com/LUPA/user/password/forgotpassword/otp | status_response , success=1, (Please reset your new password) success = 0 (Invalid OTP, please enter correct otp) | otp | UI : Completed Integration : Completed | 17/12/2018 | 22/12/2018 | 21/12/2018
| Password Reset Page | http://kaizenat.com/LUPA/user/password/forgotpassword/otp | status_response,success= 1(Sucessfully logging in takes to dashboard.),success=0 (Password do not match or email does not exist) | email, password, password_confirmation | UI : Completed Integration : Completed | 17/12/2018 | 22/12/2018 | 21/12/2018
| Dashboard |  |  |  | UI : In progress Integration : Yet to start | 21/12/2018 | 30/12/2018
| Faourite |  |  |  | UI : In progress Integration : Yet to start |  | 30/12/2018
| Product wise Dashboard |  |  |  | UI : In progress Integration : Yet to start |  | 30/12/2018
| Report license dashboard |  |  |  | Yearly UI : in progreess Integration : Pending Monthly : UI : Yet to start Integration : Yet to start Weekly : UI : yet to start Integation : yet to start Last 5 minutes : UI : yet to start Integration : yet to start |  | 30/12/2018 |  | 19/12/2018 : Weekly and last 5 minutes design section is missing in pdf
| Profile |  |  |  | UI : Completed Integration : Completed | 2018-12-26 | 28/12/2018 | 2018-12-26

## product
user | Module | URL | Method | UI | Functionality
user | Product
settting page
Cost calculations
Dyna Compare
SMTP
admin
manager

## report
user | Module | URLs | Method | UI | Functionality
user | Dashboard | http://kaizenat.com/LUPA/dashboard |  | Pending | Pending

## clarification
User | Module | URL | Method | clarification
| Dashboard | http://kaizenat.com/LUPA/dashboard | GET | Provide api for attached image. Refer screenshot-1

## screenshot
Screenshot - 1