## Sheet1
user category | page name | existing | Change | status
all users | dashboard | No vertical scroller for products, reports | Add Vertical scroller in left navigation bar | Completed
user | dashboard | on click product name not working | on clicking product name real time utilization of the product should be displayed. | Completed
| monthly click report | pie chart data overlapping | pie chart should comprise of all the 12 months data. | Completed
| yearly, monthly report | year radio buttons coming outside the chart. | year radio buttons should come inside the chart. | Completed
| All reports | All charts displaying only LSDYNA data, no option to select other products. | products radio buttons click not acceping. | Completed
| weekly report | for area chart name not displaying |  | Completed
| Favourites | name not highlited after clicking |  | Completed
| Favourites | Monhtly names are displaying two times |  | Completed
| Left navigation | when navigation closed,reports and products click not working |  | Completed | still not working for user, please cross check.
| All reports close button | close report button not working |  | Completed
| profile update | email not displaying by default. | still email is not displaying by default | Completed
| favourites | after adding monthly report to favourites, it is not displaying under favourites section. and is same for all. |  | Completed
| Recent reports | They are not displaying in order. There is a confusion in this. |  | Completed
| dashboard | Real time data utilization is wrong, we have to check together in this. |  | Completed
| dashboard | on product click dropdown is not closing automatically after selecting product. |  | Completed
| all chart types | selected chart type icon not highlighted for all the charts, only starting 4 or 5 icons are highlighting remaining not highting. |  | Completed
| favourites | data is coming but chart is empty |  | Completed
| recent reports | always yearly report name is showing whereas in the database it was the monthly report. |  | Completed
department manager | Report | after selecting monthly report, name "yearly report" is showing for scatter chart (or) bubble chart |  | Completed
| dashboard | product selection dropdown did not open at all |  | Completed
| all charts | all charts are displaying only for LSDYNA product only. |  | Completed
| all charts | shifts filter not displaying |  | Completed
| favourites | same case as the users |  | Completed
| monthly report | individual filter usernames are displayed with same color. |  | Completed
| all charts | chart type not highlighted on chart type click for all charts. |  | Completed
| dashboard | unable to click on notification icon. |  | Completed
|  | chart icon highlight not implemented for all. |  | Completed
| reports | license statistics and time statistics should be separate charts |  | Completed
|  | each chart is allowing to overlap on another chart but in those cases the chart which is already existing should either move left right, top or bottom. |  | Completed
|  | LUPA © Copyright 2018 - restrict this copyright to left navigation panel itself at the foot and remove the grey color band at the footer of the page. |  | Completed
|  | if we try to drag the chart, even the years list also coming along with it and below chart is moving downwards. |  | Completed
| dyna compares | when i select BETA_CAE response is coming but those features are not displaying but i can see them in Input->Network tab |  | Completed
| yearly report | when i select yearly report and i logged in as nayanmeher@gmail.com, then it is still loading indefinitly, i have shared the screenshots too. |  | Completed
| dyna compares | there is no dyna comparion chart page only comparison is there, but there is no comparison charts page |  | Completed
| reports | when i select this week report in time statistics, initially this week report in time statisics is highlighted but when i try filtering in the chart then the this week report in license statistics is getting highlighted. and also when i select day shift filter still the day session wise is showing. |  | Completed
| fotgot password | for the first time when i click on forgot password, the otp is empty, and i have reset the password. but when i click on forgot password again and go to otp page, then the otp is already filled with old otp. but it has be cleared and should be empty
| notification | notification red color icon is going off when i reload the page and even when i accept or reject still it is showing the same no of notifications. |  | Completed
| dyna compares | dyna compares button put it at the top navigation bar next to dashboard, favourites like cost analytics for admin. |  | out of scope
| recent reports | All recent reports are monthly reports and vertical bar chart, line chart and pie chart coming as response . but charts dispaying are lsdyna all 3 yearly report only. |  | Completed
|  | here the first one is weekly and second one is yearly. but in the last image both report names are same = check whatsapp images for reference |  | Completed
| favourites | monthly reports is being received but chart not displaying. |  | Completed
|  | i cleared the favourites table and tested this. i think the yearly report API is not taking but filter years list API is taking. |  | Completed
| report and products | It is like first time when i login, i am able to select. after selecting any report and then trying to select other product it is not allowing and again when i click on products dropdown and then when i click i select product then its selecting. But when i click products dropdown again, then the report which i selected is disppearing. |  | Completed
|  | then the report which i selected is going away. if i want to compare the yearly report of LSDYNA and yearly report of ALTAIR then how to compare both of them. |  | Completed
| dyna compares | beta_cae features are coming as a response but not displaying |  | Completed
|  | all charts not displaying only one chart is displaying after submit. |  | Completed
admin | in dropdown filters | overall option is missing, after selecting any other months and if i again want to see overall then there is no option in dropdown for overall. |  | Completed
| dashboard | real time utilization - if there is no data, then a default chart with horizontal line should be displayed, but that is missing for all 3 users. |  | Completed
| reports | when i expand a chart then it is acquiring full page but when i resize it to half page, then the chart below is not coming on to top to adjust itself. |  | Completed
| recent reports | There are some issues in recent reports, its not coming in order. |  | Not able to reproduce
| cost analytics | cost analytics button not highlighted after clicking |  | Completed
chart types not working in cost analytics
drag and drop - cost analytics not working.
Please test entire cost analytics page from your end because many functioanlities are missing.
And also chart colors for all the three users, Names of the charts are missing.
| reports | separate charts for time statistics and license statistics for all reports. |  | Completed
| settings page | if we click delete department, then the department is deleting without any confirmation. |  | Completed
| settings page - department manager tab | block, confirm, delete all needs a confirmation before performing an action. |  | Completed | It was discussed only delete needs confirmation
| profile update | submit button at the centre of the form and instead of two separate forms, it should be single form with name, email, password, confirm password, and submit button. |  | Completed
|  | when we click on profile update then by default it is asking for id field is required. |  | Completed
| cost calculator | should not allow deleting purchase item without confirmation |  | Completed
|  | amc_renewel is missing in license types dropdown. |  | Completed
| favourites | there is some issue in favourites, i think we have to look into it. |  | Completed
| notifications | No notification message not displaying for admin, please check. |  | Completed
| yearly report and same for all reports | yearly report for admin = i selected year and department type but still the chart is not changing.
Testing on 12-2-2019, tuesday
User | Page name | Changes required | Status
Admin | dashboard | blank chart for live chart in dashboard, not displaying. | Completed
| reports | the drag function is coming below (in the image b/w two charts ) indefinitely, please restrict that to chart itself. (refer whatsapp for image)
Altair weekly report, years and charts alignment issue.
after selecting beta_cae product, i am trying to select this week report, but yearly is being selected. even when i clicked on this week report (refer video in whatsapp)
the last two charts are BETA_CAE yearly, monthly, pie charts, but they are displaying differently, in recent report in the second scrrenshot attached. refer (whatsapp screenshot)
Heat map for all charts not implemented.
unable to select polar chart, and one more chart before it, because of overlapping of year
year filter is not displaying for weekly, so unable to understand for which year this months represent.
| important | For all filters user, department, the different types of charts are not displaying for all reports for both admin, department manager
The chart is not draggable, only indicator is coming below (refer screenshot in whatsapp)
| favourites | while adding yearly report to favourites, The API is different, you are sending years filter api you are sending, so as a response you are getting only years list and the first chart in this image is displaying, please try adding yearly report to favourites and check, (refer whatsapp screenshot)
while adding yearly report to favourites, The API is different, you are sending years filter api you are sending, so as a response you are getting only years list and the first chart in this image is displaying, please try adding yearly report to favourites and check, (refer whatsapp screenshot)
please check this video. (check for video with this name) favourites section changes.
| recent reports | please check this recent reports video. (check for video with this name) recent reports section changes.
| cost analytics | For first 2 charts chart types are not working.
For all charts overall, button should be there even after selecting one option, if they want to view overall, option should be made available.
names of the values on chart bar hover with percentage symbol, different names, for each graph, i will tell the names, of each charts.
refresh chart icon is taking lot of time to load again.
in cost analytics i selected only month, even though it is accepting and it is sending year as jan, that's why chart is not displaying. and also month shoulb be 00 format not single digit. (refer whatsapp image for reference)
For all the charts, in cost analytics, month value should be in 00 format, ex- for jan = 01, this should be the format, please check once for all charts in cost anaticis. (refer schreen shot in whatsapp)
For both charts name are showing solidworks, and also there is one more charts below named solidworks, i think chart names are mis matching.
if months is not selected then send the month value as blank, please dont send 0 as value.
on chart icon click, highlight not happening, please check.
chart types not working in cost analytics
drag and drop - cost analytics not working.
Please test entire cost analytics page from your end because many functioanlities are missing.
And also chart colors for all the three users, Names of the charts are missing.
| notification | The Transferred user details not showing in the notification |  | Can you please replicate the issue
|  | when a notification comes, for the first time it is displaying, but when i refresh the page, without accepting or rejecting then after refresh it is not displaying. but notification status is still 0 only. | Completed
|  | if we reject or accept user then it is loading indefinityly and not loader not stopping, |  | Can you please replicate the issue
| cost calculator | amc_renewal is missing from dropdown, please add amc_renewel | Completed
|  | In cost calculator page, the date time format is not correct, please check |  | Can you please give the format
I
| Settings | in add department section, there is a button edit department, which is not working, and also remove edit button, becuase there is no API for that. | Completed
11 : 00 AM 13-02-2019
User | Page name | Changes required | Status
admin | reports important | when i select one product and click on any report, it is displaying as per that, but when i select another product and select the same report then in the same chart it is replacing with new content, but new chart is not creating, so in this case if he wants to compare two products of one report he cannot compare.(shared whatsapp video). ( This should be the same for all report types). | Completed
| dashboard | blank chart for live chart not displaying. | Completed
|  | please change Total license used on hourly basis to total no of hours used. in all time statistics report. | Completed
|  | beta cae monthly report overall first works fine, but when i go back to overall from individual, its not showing the chart | Completed
it is same case for all charts, and also overall, individual radio buttons are not getting checked, for many charts, please check
In This week report, the filters day session, shift sessions, are displayed only for first time, but when i change to different chart types and coming again back to line chart also, they are not displaying. please check. (shared whatsapp video).
|  | The filters are moving along with drag icon on right side. in this week report | Not able to reproduce
|  | This week reports(BETA CAE, etc) are creating many times i think, the same chart is created two times, please check the video, | Completed
|  | Heat maps for all report charts | As discussed earlier heat map chart wil not work for all format
| important | The same issue as user, for new charts, the existing chart name is taking. It is there for admin also, please check. | Completed
department manager | favourites | Favourites for department manager, Same as admin, please check.(refer video sent in whatsapp).
| dashboard | blank chart for live chart not displaying. | Completed
| recent reports | Recent reports for department manager , It is same as admin, i think if you do changes for admin, then the same can be used for dept amanger also i believe, please check video.(refer whatsapp video). | Completed
| dashboard | For last 5 minutes and last 24 hours, the response is received, but the loader is still rotating.( refer whatsapp video) | Completed
|  | When i accept or reject it is showing the message but it is not getting removed from there and also when i reject the message is showing in red color, please check. | Completed
| notifications | After accepting or rejecting the no of notifications should be removed because if it displays again and when they accept or reject again, for each click, one entry is inserting into database, so after each click, notifications has to be removed from there. | Completed
| profile update | Department manager profile update, it is asking for id field. please check. | Completed
| dyna compares | In dyna compares, please check in the video, after selecting MSC, for the first time i addedd two features and one feature left, and again i wanted to add remaining one feature when i checked it and addedd then it is taking all 3 features, please check the video, for better understanding.
Try arranging the features because they are overlapping.
please check whether features exists condition before adding to compares
when i select this week report in time statistics, initially this week report in time statisics is highlighted but when i try filtering in the chart then the this week report in license statistics is getting highlighted. and also when i select day shift filter still the day session wise is showing.
| reports | heat maps are missing for all charts for all reports
| important | when i select one product and click on any report, it is displaying as per that, but when i select another product and select the same report then in the same chart it is replacing with new content, but new chart is not creating, so in this case if he wants to compare two products of one report he cannot compare.(shared whatsapp video). ( This should be the same for all report types). | Completed
| all reports | monthly report, department manager = overall, individual radio buttons are not checked for first time, but after two clicks it is showing as checked. | Completed
| reports | year filter is not displaying for weekly, so unable to understand for which year this months represent. year radio buttons not displaying
In This week report, the filters day session, shift sessions, are displayed only for first time, but when i change to different chart types and coming again back to line chart also, they are not displaying. please check. (shared whatsapp video).
Pie charts and bubble charts, scatter charts are not displaying for many charts, please cross check before uploading, and if any changes required from backend, please inform.
From dyna compares page, it is not allowing to select product, the dropdown is closed
| important | The same issue as user, for new charts, the existing chart name is taking. It is there for admin also, please check.
user | favourites | The favourites page is same as the admin, dept. please check. | Completed
| dashboard | blank chart for live chart not displaying. | Completed
| recent reports | And recent reports also the same, please check. | Completed
| profile update | user email should automatically filled up from server response. | Completed
| reports | Same reports are displaying two times. for user (refer screenshot sent in whatsapp).
user -> yearly report, Please check, multiple products name in a single report. (refer video sent in whatsapp).
| important | For user, when another product charts are already displaying when we select different product and try for same report as exsisting, then they are displaying but when we try to select other chart types, then the product itself is changing as the existing charts. please check. (refer whatsapp video). | Completed
10:53 14/02/2019 Testing changes
| department manager | I think its width is restricted to half, please allow full width. in dyna compares, for each chart. Time = 10.52AM
| admin | TIME = 10.41 AM, This one is very important harish, the existing chart are getting renamed with new chart product names. because of that same reports for same product name are created mutliple times. please check.
| admin | TIME = 11.55 AM Because of this i am unable to check other features, please check this video also.
| admin | TIME = 12 AM and also for pie charts, the percentage is not being displayed, please check that.
05:18 19/02/2019
| department manager | 05:17 In the MSC/yearly report year 2016 shows but it is not displaying as radio button at the top. and it is displaying trace 0 please check that.
05:20 when i clicked on 2019 radio button the years list radio buttons disappeared.
05:47 I think this error still not resolved, please check this.
05:59 The years radio buttons are getting disappeared when we select one radio button. please check.
06:10 The old issues are still pending, please check.
2019-02-20
| for all users | 07:23 please check this video. when i select altair for first time and select yearly report. but lsdyna is coming and when i add it to favourites LSDYNA report is adding instaed of altair and when i go back and tried to select altair and again it is selecting as LSDYNA and to check when i select MSC and yearly report even then also only LSDYNA is displaying. please check.
|  | 07:48 horizontal bar chart and scatter charts and polar charts are not displaying in favourites after adding also. please check. | Completed
All the charts are having the same same colours please use dynamic colours.
| user - monthly report | 09:53 The data is coming but it is not being displayed please check.
| user - weekly report | 09:56 For user, the alignment issue is still there.
| user- weeklly report | 10:15 User - weekly report, for pie chart data is coming but it is not being displayed
| user- weeklly report | 10:23 User - weekly report data is being received but not displaying. please check.
10:33 User - weekly report years filter for is working only for polar chart and line chart, stacked chart and for other charts it is not displaying, please check.
| user | 10:49 monthly chart - favourites - horizontal bar chart not displaying properlly.
| user - favourites | i have added many charts to favourites but only 6 are displaying. | Completed
and also when i tried to select any other report other than year report it is getting clicked by default even though i click on other reports.
Heat maps are not displaying for any of the charts.
and getting error when we add more no of favourites reports.
| user - this week report | 12:50 For This week report, data is being received but it is dispalying as monthly report and also values are not correct, please check.
| user - this week report | 12:53 I have inserted some dummy data for this week report. please check for line chart and all remaining charts.
department manager | favourites | loader not displaying in favourites page for all users.
text message when report is addedd to favourites. place it at the top right of the screen.
not displaying all the favourites, displays only some report charts.
when i add monthly, weekly, this week reports to favourites, they are displayed in the favourites section but they are inserting into database and also received in the response.
| weekly, this week report. | 06:01 he users list is getting disappeared, please check.
polar chart is missing for weekly, this week report user filters. pie chart and box plot are not implemented.
| weekly report | No year filters for weekly report in individual fiter.
chart is not displaying as per year radio button and selected chart type, it is displaying only vertical bar chart always.
| monthly report | pie chart not displaying. | Data format is wrong
admin | monthly report | 06:45 Please check monthly report filters types, because that looks complete wrong data.
Starts from here
Final list of changes. DATE - 22/02/2019
user | page | changes | status | Status response
all users | Dashboard | Blank chart for live chart not displaying. | Completed | But for us not displaying. please verify in multiple machines
admin |  | 09:27 Alignment issue for last 5 minutes and last 24 hours. | Completed
|  | please remove YTD text from live chart. keep only ALL button | Completed
| Dashboard - saturation | Values not displaying on hover. and also add different color in place default blue color. |  | Data not available
| Dashboard | When i click on any product in products list then the dashboard is still shows highlighted, plase dont hightlight that, since it is a particular product and also, below the selected product should be selected in last 5 minutes, todays, saturation. | Completed
|  | 10:01 Live chart data is being received, but not rendering in the chart. please check. | Completed
|  | [10:03, 10:06] And also the date shows that sunday jan 18, but it is suppossed to be todays date and time. If any changes required from backend please inform. and it is displaying negative values also, please check. | Not able to reproduce | please provide a valid timestamp, highchart will render based on what you have provided
|  | 10:10 When i reload the page, For last 5 minutes and last 24 hours, the data is displaying but it is not showing for which product that data belongs to. it should display the default product name which you are sending. | Completed
|  | Instead of dropdown for saturation, display radio buttons, so that all three will be same in size. | Moving this change to next version
|  | Remove Highcharts.com watermark on live chart | Completed
|  | 10:27 On any other product click other than LSDYNA the chart still shows LSDYNA data instead of blank chart. | Completed
| reports | 10:35 When i select a product name and try to select any report then by default the LSDYNA yearly report is dispalying, and again i have to do the same selections again. please check this. | Completed
|  | When i add to favourites, there is no message saying whether it is added or not. please add it. | Completed
|  | MSC - line chart added to favourites, and data received at favroutes, but not displaying. | Completed
|  | 10:42 Unable to zoon in, when trying to hold the mouse click even the chart itself allowing to reposition please check. | zoom in feature is not available in polar chart
10:45 Box plot chart not displaying, please check,
| all reports | 01:13 In the overall department name and user names are displaying sometimes, when i change from individual to overall, please check. | Completed
| 2019-02-25 | 7:02 This is one of the serious issue, please check, The first chart is yearly report and second chart is monthly report. But actually the charts looks like got interchanged, you will find it in the video. | Completed
| 2019-02-25 | 07:14 I think it is storing the sent values and then using the same values for the next request, This one is also major, please check. | Completed
| 2019-02-25 | 07:18 This is also major one check. please | Completed
| 2019-02-25 | 07:09 The above issue looks the same for all reports of the same product. | Completed
| All reports | Heat map chart not impleted yet. | heat map will get implemented in this version
|  | Please use dynamic colours, The existing colors are same for all reports and charts and looks boring. use my color code. | Will be done in next phase
|  | 11:05 In the chart it is displaying as trace 0 instead of year names, please check the chart is same for all remaining charts in filter. | Completed
|  | 11:08 For user filter also, the same charts display is same as department filter, please check. | Completed
|  | 11:16 admin - yearly report, resize alignment issue | Completed
|  | 11:18 filters overlapping with above chart. | Completed
|  | 11:24 Box plot chart not displaying, if it is from backend, i will check it. But for reference check, i am updating here. | Completed
|  | 11:37 Please check this error in user filter monthly report: | Completed
|  | Please check this error in department filter monthly report: different chart types not displaying. showing as trace 0 | Completed
11:58 The same as above, but for reference sending this video.
12:01 since no radio buttons are checked, we are unable to find out for which year this data represent.
12:03 Pie chart not dispalying. and it displays monthly report but actually it is weekly report.
12:05 Box plot line chart not displaying, please check.
12:07 This blue color for month indicator and in the chart also not looking good at all, please remove and try different one.
12:29 Please check, The same stacked chart is repeating multiple charts.
|  | 12:35 ovelapp and resize icon at different position. | Completed
12:37 I think here, after clicking individual filter, department is selected but it is going for filter user so the chart not displaying.
12:40 Since no department is selcted, we are unable to check, for which department this data belongs to. and also year filter not there, please add it.
|  | 12:43 Box plot line chart, pie chart not displaying. both in dept and user filter. | Data format issue
polar chart not added for all filters in reports.
Day session wise and Day shift wise not addedd for filters in This week report.
| 2019-02-27 | 10:16 Years and x-label overlapping.
10:20 Weekly all radio buttons are getting clicked.
| Important - 27/02/2019 | 10:30 1. Some charts are not displaying at all, if the format is wrong, please provide the correct format so that we will change it. 2. For individual filters the charts not displaing at all and the api is different from what it is supposed to send for filters and also the filter values are sending incorrectly, when i click user then the department name is sending, and interchanging, please check thoroughly from your end before uploading. Please check for weeklly report for dept and user also.
11:58 I think, This week and weekly report are inter connected. and In this week report years 2016 2017 2019 are displaying. Please check.
Weekly report is not yet completed fully, please do proper testing after completion.
12:01 Please resolve this issue.
11:43 Add to favourites message not displaying in some cases and polar chart - i think it is by default coloured, please remove that. and horizontal and buble charts are not displaying properly at recent reports also.
Polar charts not displaying in favourites, but it shows that they are already added.
01:13 default checkbox not checked.
| All reports 25/02/2019 | 01:01Individual filters for all reports Individual filters for all reports, please do testing from your end and then upload. In all charts trace 0 is displaying, please check. They are completely wrong please check once.
| This week report | Different chart types for overall not displaying, please check.
1:20 Other labels are not displaying, afternoon and evening, also the resize alignment icon is at different position, please check. and also day shift and shift wise filters not added,
1:23 When i select user filter then the department and user filter both disppeared, please check.
This week report, For filters different types of charts not displaying, please check.
|  | 1:28 The selected report not highlighting. in the left navigation panel | Completed
| Recent Reports | 1:32 In Recent reports, all the charts displaying the same chart eventhough the chart types recieved are different. | Completed
|  | Loader not displaying for recent reports. | Completed
12:38 Horizontal bar chart displaying differently than usual.
| For Time statistics reports only for all users. | Please change the Text - Total license used on hourly basis TO Total no. of hours used | Completed
1:48 Check this, The first chart is license statistics and second is time statistics, but they are sending request to same API, i think please chek.
3:13 I think both are interlinked, please check.
| favourites | display loader until page fully loads. and displays charts | Completed
I think in this chart two chart types are overlapping or two datas are merged in one.
03:57 Horizontal bar chart is not showing properly in favourites. The first one is LSDYNA but displaying as MSC,
|  | text message when report is addedd to favourites. place it at the top right of the screen. | Completed
| 2019-02-27 | 27/2/2019 1. In favourites the horizontal and bubble chart are not proper and polar shows it is addedd to favourites but not displaying in the favourite section. 2. The monthly report is displaying only line chart and not displaying other charts, and also In the filters there are some changes required, please check the full video.
| cost analytics | For first 2 charts chart types are not working. | Completed
|  | For all charts overall, button should be there even after selecting one option, if they want to view overall, option should be made available. | Completed | Not added please check.
|  | names of the values on chart bar hover with percentage symbol, different names, for each graph, i will tell the names, of each charts. | Completed
|  | refresh chart icon is taking lot of time to load again. | Completed
|  | in cost analytics i selected only month, even though it is accepting and it is sending year as jan, that's why chart is not displaying. and also month shoulb be 00 format not single digit. (refer whatsapp image for reference) | Completed
|  | For all the charts, in cost analytics, month value should be in 00 format, ex- for jan = 01, this should be the format, please check once for all charts in cost anaticis. (refer schreen shot in whatsapp) and month and year values should be integers. | Completed
|  | For both charts name are showing solidworks, and also there is one more charts below named solidworks, i think chart names are mis matching. | Completed
|  | if months is not selected then send the month value as blank, please dont send 0 as value. | Completed
|  | on chart icon click, highlight not happening, please check. | Completed
|  | chart types not working in cost analytics | Completed
|  | drag and drop - cost analytics not working. | Completed
| 2019-02-27 | Please test entire cost analytics page from your end because many functioanlities are missing. | Completed
12:31 On type of license click - The month value is passing to server is different, it should be 00 format.
percentage symbol on chart over not displaying.
product names are not being displayed.
12:51 and also for 2019 only jan and feb are displaying, can you please let me know, wether they are static or from server.
1:04 For department manager - notification reducing in number after accepting or rejecting user is done, but it is not implemented for admin.
12:48 Radio buttons are by default checked, and also the feature names are overlapping and full screen icon not functioning, please check.
1:23 At many places the name of the month still exists, please cross verify for all charts in cost analytics.
1:08 And also on page reload the notifications are disappearing, eventhough the admin has not clicked on anything.
1:01 User details in notification not displaying. please check
| dyna compares | 1:18 Invalid date time format, please check for cost calculator
overall option not give for all charts in cost analytics
|  | And also chart colors for all the three users, Names of the charts are missing. | Completed
|  | cost analytics charts cannot be addedd to favourites, pelase remove favourites icon. | Completed
| 2019-02-25 | 04:24 If the year values are static values, then please remove them. | Completed
|  | There should be no defined static values in any page in case if there are then remove those and will send required values from backend , i mean like names, year values, etc. | Completed
|  | feature names are overlapping, | Completed
|  | 04:34 The loader is misplaced while loading and also the reload button is taking so much time. please check for remaining charts also. | Completed
|  | 04:40 on full screen icon click this error is displaying, please check. | Completed
|  | 04:46 On chart resize the charts are overlapping. and resize icon mispositioned | Completed
|  | 04:38 The loader is still loading below check. | Completed
|  | 05:04 For some charts resize icon not working, when i drag the resize icon, only the icon is coming but no chage in the chart. and only one chart resize option is working. | Completed
|  | 05:12 on radio buttons click, Solid works name displaying at the centre of page, Instead for first chart name = Total Software expenditure. for second chart. Total software utilization. Please rename them and remove Total expenditure at the top of charts for thesess two. | Completed
|  | For features list chart, the name should be "Per feature Total utilization". | Completed
| favourites | The resize icon only first one is working and remaining not working and also check the position of resize icon. | Completed
user | Page | 2019-02-24
| time statics and license statics | 08:51 I think the license statistics and time statistics are calling the same api and the values also the same, please check.
Even the individual filters are also the same issue, plese check and test from your end and then upload, now i am not checking the remaining time statistics part (monthly, weekly, this week).
08:56 The years filter are changing like the same for both, please check.
2019-02-25
| all reports | Product names on top of the charts are mis matching, please cross verfy for all charts and reports for all users also, please check.
| dasbhoar live chart | 03:34 For live chart the username sennding is different from actual user login. please check. | Completed
2019-02-26
department manager | recent reports | 11:52 Department manager - recent reports different charts not displaying only single format charts are displaying, please check.
| reports | 1:08 In the first chart The year selected is different and the values displaying is different, please check.
1:22 The year value is taking for all reports irrespective of chart product name report name. year 2016, 2019 does not exist for MSC and altair but it is taking :the year values of LSDYAN after click.
1:31 For all charts individual filters the resize icon position is misplaced. check for all charts.
2:44 When we click on years radio buttons, the current chart is not displaying but always line chart is displaying, please pass the current selected chart name.
3:02 The Issues that were there for admin, are also present in dept manager report, please test from your end before uploading to server and also check for user also, i am testing for user.
3:19 In all reports, after checking charts in individual filter when i come back to overall filters then the charts are not displaing properly, it shows trace 0, please check.
3:26 The first chart is yearly chart and second chart is monthly chart. But because of the monthly polar chart, the yearly polar chart is also changing, please check.
3:31 x axis title and years radio button overlapping.
3:35 Please check the year radio buttons, pie chart, and polar chart that is linked to other reports polar chart and also the chart type upon clickiing radio buttons,
3:41 If in one chart if it does not receive any data and when we check other reports charts then even those reports also it is not receiving data and shows blank for all charts, please check this video.
3:48 Monthly is not displaying any data but data is recived and for polar chart - if i click on monthly report - polar chart and then again click on yearly report - polar chart , Then it is displaying monthly polar chart in place of yealry polar chart.
4:28 Same as above issue, The charts of monthly report are displaying in yearly report chart after clicking.
All users | favourites | loader for favourites section becuase currently it looks like no data found.
Horizontal bar charts and bubble charts are not properly displaying.
2:41 resize functionalinty not working properly for admin, dept, user, and also please display whether it is time statics or license statistics below the product name and report name on the charts.
2:44 and also if there are any filter_user, filter_year, filter_department, values in response please display those also.
2:56 There are some changes in weekly report, please check. The API are different as per me. and also the years radio buttons and text overlapping.
3:03 Both license statistics an time statistics are inter linked, The same is for admin and user also, please check.
3:10 Time statistics and license statistics are linked for all reports for all users, please cross verify before uploading to server.
3:35 The horizontal scroll bar is implemented, because there will be so many features, if it increases then auto horizontal scroll bar should come.
3:43 Please use different colours
3:47 I clicked on individual filters and then selected time sttistics, the charts itself opens for individual filters and with some radio buttons selected, because i have open individual filters of license statistics of same product and report. please check.
3:55 For Time statistics x-label is different from what currently exists.
4:03 There are inter linking between many charts, i am unable to understand which is linked to which chart, please cross verify before new deployment.
user | favourites | 4:16 When favourites is empty, the loader is still loading indefinitely.
please change the color of the text message to different color, when favourites is added..
4:24 years are repeating in the charts. and i think two different charts are displayed in one graph.
| profile | email field should be automatically filled up.
| reports | 4:35 Many same issues are existing for user also, please cross check.
4:41 In This week report, the report names are changing and also the pie chart and some charts are not displaying, please check.
4:44 Time statistics are also interlinked, please cross verif for remaining reports for license and time statistics
| fotgot password | for the first time when i click on forgot password, the otp is empty, and i have reset the password. but when i click on forgot password again and go to otp page, then the otp is already filled with old otp. but it has be cleared and should be empty
all users | weekly report | year filter is not displaying for weekly, so unable to understand for which year this months represent.
| Side menu panel | when i select this week report in time statistics, initially this week report in time statisics is highlighted but when i try filtering in the chart then the this week report in license statistics is getting highlighted. and also when i select day shift filter still the day session wise is showing.
| This week report | In This week report, the filters day session, shift sessions, are displayed only for first time, but when i change to different chart types and coming again back to line chart also, they are not displaying. please check.
| All reports | Pie charts and bubble charts, scatter charts are not displaying for many charts, please cross check before uploading, and if any changes required from backend, please inform.
loader not displaying in favourites page for all users.
polar chart is missing for weekly, this week report user filters. pie chart and box plot are not implemented.
No year filters for weekly report in individual fiter.

## Sheet2
Final list of changes. DATE - 22/02/2019
user | page | changes | status | Status response
all users | Dashboard | Blank chart for live chart not displaying. | Completed | But for us not displaying. please verify in multiple machines
admin |  | 09:27 Alignment issue for last 5 minutes and last 24 hours. | Completed
admin |  | please remove YTD text from live chart. keep only ALL button | Completed
admin | Dashboard - saturation | Values not displaying on hover. and also add different color in place default blue color. |  | Data not available
admin | Dashboard | When i click on any product in products list then the dashboard is still shows highlighted, plase dont hightlight that, since it is a particular product and also, below the selected product should be selected in last 5 minutes, todays, saturation. | Completed
admin |  | 10:01 Live chart data is being received, but not rendering in the chart. please check. | Completed
admin |  | [10:03, 10:06] And also the date shows that sunday jan 18, but it is suppossed to be todays date and time. If any changes required from backend please inform. and it is displaying negative values also, please check. | Open | Not able to reproduce. please provide a valid timestamp, highchart will render based on what you have provided
admin |  | 10:10 When i reload the page, For last 5 minutes and last 24 hours, the data is displaying but it is not showing for which product that data belongs to. it should display the default product name which you are sending. | Completed
admin |  | Instead of dropdown for saturation, display radio buttons, so that all three will be same in size. | Closed | Moving this change to next version
admin |  | Remove Highcharts.com watermark on live chart | Completed
admin |  | 10:27 On any other product click other than LSDYNA the chart still shows LSDYNA data instead of blank chart. | Completed
admin | reports | 10:35 When i select a product name and try to select any report then by default the LSDYNA yearly report is dispalying, and again i have to do the same selections again. please check this. | Completed
admin |  | When i add to favourites, there is no message saying whether it is added or not. please add it. | Completed
admin |  | MSC - line chart added to favourites, and data received at favroutes, but not displaying. | Completed
admin |  | 10:42 Unable to zoon in, when trying to hold the mouse click even the chart itself allowing to reposition please check. | Completed | zoom in feature is not available in polar chart
admin |  | 10:45 Box plot chart not displaying, please check, | Completed
admin | all reports | 01:13 In the overall department name and user names are displaying sometimes, when i change from individual to overall, please check. | Completed
admin | 2019-02-25 | 7:02 This is one of the serious issue, please check, The first chart is yearly report and second chart is monthly report. But actually the charts looks like got interchanged, you will find it in the video. | Completed
admin | 2019-02-25 | 07:14 I think it is storing the sent values and then using the same values for the next request, This one is also major, please check. | Completed
admin | 2019-02-25 | 07:18 This is also major one check. please | Completed
admin | 2019-02-25 | 07:09 The above issue looks the same for all reports of the same product. | Completed
admin | All reports | Heat map chart not impleted yet. | Closed | heat map will get implemented in this version
admin |  | Please use dynamic colours, The existing colors are same for all reports and charts and looks boring. use my color code. | Closed | Will be done in next phase
admin |  | 11:05 In the chart it is displaying as trace 0 instead of year names, please check the chart is same for all remaining charts in filter. | Completed
admin |  | 11:08 For user filter also, the same charts display is same as department filter, please check. | Completed
admin |  | 11:16 admin - yearly report, resize alignment issue | Completed
admin |  | 11:18 filters overlapping with above chart. | Completed
admin |  | 11:24 Box plot chart not displaying, if it is from backend, i will check it. But for reference check, i am updating here. | Completed
admin |  | 11:37 Please check this error in user filter monthly report: | Completed
admin |  | Please check this error in department filter monthly report: different chart types not displaying. showing as trace 0 | Completed
admin |  | 11:58 The same as above, but for reference sending this video. | Completed
admin |  | 12:01 since no radio buttons are checked, we are unable to find out for which year this data represent. | Completed
admin |  | 12:03 Pie chart not dispalying. and it displays monthly report but actually it is weekly report. | Completed | Format issue. format should be like other report type.
admin |  | 12:05 Box plot line chart not displaying, please check. | Completed
admin |  | 12:07 This blue color for month indicator and in the chart also not looking good at all, please remove and try different one. | Closed | In-built colors are there according months. if we change so many places it will impact
admin |  | 12:29 Please check, The same stacked chart is repeating multiple charts. | Completed
admin |  | 12:35 ovelapp and resize icon at different position. | Completed
admin |  | 12:37 I think here, after clicking individual filter, department is selected but it is going for filter user so the chart not displaying. | Completed
admin |  | 12:40 Since no department is selcted, we are unable to check, for which department this data belongs to. and also year filter not there, please add it. | Completed
admin |  | 12:43 Box plot line chart, pie chart not displaying. both in dept and user filter. | Completed | Data format issue
admin |  | polar chart not added for all filters in reports. | Completed
admin |  | Day session wise and Day shift wise not addedd for filters in This week report.
admin | 2019-02-27 | 10:16 Years and x-label overlapping. | Completed
admin |  | 10:20 Weekly all radio buttons are getting clicked. | Completed
admin | Important - 27/02/2019 | 10:30 1. Some charts are not displaying at all, if the format is wrong, please provide the correct format so that we will change it. 2. For individual filters the charts not displaing at all and the api is different from what it is supposed to send for filters and also the filter values are sending incorrectly, when i click user then the department name is sending, and interchanging, please check thoroughly from your end before uploading. Please check for weeklly report for dept and user also. | Completed
admin |  | 11:58 I think, This week and weekly report are inter connected. and In this week report years 2016 2017 2019 are displaying. Please check. | Completed
admin |  | Weekly report is not yet completed fully, please do proper testing after completion. | Completed
admin |  | 12:01 Please resolve this issue. | Completed
admin |  | 11:43 Add to favourites message not displaying in some cases and polar chart - i think it is by default coloured, please remove that. and horizontal and buble charts are not displaying properly at recent reports also. | Completed
admin |  | Polar charts not displaying in favourites, but it shows that they are already added. | Completed
admin |  | 01:13 default checkbox not checked. | Completed
admin | All reports 25/02/2019 | 01:01Individual filters for all reports Individual filters for all reports, please do testing from your end and then upload. In all charts trace 0 is displaying, please check. They are completely wrong please check once. | Completed
admin | This week report | Different chart types for overall not displaying, please check. | Completed
admin |  | 1:20 Other labels are not displaying, afternoon and evening, also the resize alignment icon is at different position, please check. and also day shift and shift wise filters not added,
admin |  | 1:23 When i select user filter then the department and user filter both disppeared, please check. | Completed | when I hit below url I am getting response as [{"favourite":false,"license":[{"morning":[0,0,0,0,0,0,0]},{"afternoon":[]},{"evening":[]}]}] http://kaizenat.com/LUPA/admin/this_week_licenses_used_dept_filter. Response value for afternoon should not be empty. Please change
admin |  | This week report, For filters different types of charts not displaying, please check.
admin |  | 1:28 The selected report not highlighting. in the left navigation panel | Completed
admin | Recent Reports | 1:32 In Recent reports, all the charts displaying the same chart eventhough the chart types recieved are different. | Completed
admin |  | Loader not displaying for recent reports. | Completed
admin |  | 12:38 Horizontal bar chart displaying differently than usual. | Completed
admin | For Time statistics reports only for all users. | Please change the Text - Total license used on hourly basis TO Total no. of hours used | Completed
admin |  | 1:48 Check this, The first chart is license statistics and second is time statistics, but they are sending request to same API, i think please chek. | Completed
admin |  | 3:13 I think both are interlinked, please check. | Completed
admin | favourites | display loader until page fully loads. and displays charts | Completed
admin |  | I think in this chart two chart types are overlapping or two datas are merged in one.
admin |  | 03:57 Horizontal bar chart is not showing properly in favourites. The first one is LSDYNA but displaying as MSC, | Completed
admin |  | text message when report is addedd to favourites. place it at the top right of the screen. | Completed
admin | 2019-02-27 | 27/2/2019 1. In favourites the horizontal and bubble chart are not proper and polar shows it is addedd to favourites but not displaying in the favourite section. 2. The monthly report is displaying only line chart and not displaying other charts, and also In the filters there are some changes required, please check the full video.
admin | cost analytics | For first 2 charts chart types are not working. | Completed
admin |  | For all charts overall, button should be there even after selecting one option, if they want to view overall, option should be made available. | Completed | Not added please check.
admin |  | names of the values on chart bar hover with percentage symbol, different names, for each graph, i will tell the names, of each charts. | Completed
admin |  | refresh chart icon is taking lot of time to load again. | Completed
admin |  | in cost analytics i selected only month, even though it is accepting and it is sending year as jan, that's why chart is not displaying. and also month shoulb be 00 format not single digit. (refer whatsapp image for reference) | Completed
admin |  | For all the charts, in cost analytics, month value should be in 00 format, ex- for jan = 01, this should be the format, please check once for all charts in cost anaticis. (refer schreen shot in whatsapp) and month and year values should be integers. | Completed
admin |  | For both charts name are showing solidworks, and also there is one more charts below named solidworks, i think chart names are mis matching. | Completed
admin |  | if months is not selected then send the month value as blank, please dont send 0 as value. | Completed
admin |  | on chart icon click, highlight not happening, please check. | Completed
admin |  | chart types not working in cost analytics | Completed
admin |  | drag and drop - cost analytics not working. | Completed
admin | 2019-02-27 | Please test entire cost analytics page from your end because many functioanlities are missing. | Completed
admin |  | 12:31 On type of license click - The month value is passing to server is different, it should be 00 format. | Completed | When you click initially , month value will be sent as ""
admin |  | percentage symbol on chart over not displaying. | Completed | If bar height is very less then percentage will not be visible properly
admin |  | product names are not being displayed. | Completed
admin |  | 12:51 and also for 2019 only jan and feb are displaying, can you please let me know, wether they are static or from server. | Completed
admin |  | 1:04 For department manager - notification reducing in number after accepting or rejecting user is done, but it is not implemented for admin. | Completed
admin |  | 12:48 Radio buttons are by default checked, and also the feature names are overlapping and full screen icon not functioning, please check. | Completed
admin |  | 1:23 At many places the name of the month still exists, please cross verify for all charts in cost analytics. | Completed | if it still exists let me know the product name
admin |  | 1:08 And also on page reload the notifications are disappearing, eventhough the admin has not clicked on anything. | Completed
admin |  | 1:01 User details in notification not displaying. please check | Completed
admin | dyna compares | 1:18 Invalid date time format, please check for cost calculator
admin |  | overall option not give for all charts in cost analytics | Completed
admin |  | And also chart colors for all the three users, Names of the charts are missing. | Completed
admin |  | cost analytics charts cannot be addedd to favourites, pelase remove favourites icon. | Completed
admin | 2019-02-25 | 04:24 If the year values are static values, then please remove them. | Completed
admin |  | There should be no defined static values in any page in case if there are then remove those and will send required values from backend , i mean like names, year values, etc. | Completed
admin |  | feature names are overlapping, | Completed
admin |  | 04:34 The loader is misplaced while loading and also the reload button is taking so much time. please check for remaining charts also. | Completed
admin |  | 04:40 on full screen icon click this error is displaying, please check. | Completed
admin |  | 04:46 On chart resize the charts are overlapping. and resize icon mispositioned | Completed
admin |  | 04:38 The loader is still loading below check. | Completed
admin |  | 05:04 For some charts resize icon not working, when i drag the resize icon, only the icon is coming but no chage in the chart. and only one chart resize option is working. | Completed
admin |  | 05:12 on radio buttons click, Solid works name displaying at the centre of page, Instead for first chart name = Total Software expenditure. for second chart. Total software utilization. Please rename them and remove Total expenditure at the top of charts for thesess two. | Completed
admin |  | For features list chart, the name should be "Per feature Total utilization". | Completed
admin | favourites | The resize icon only first one is working and remaining not working and also check the position of resize icon. | Completed
user | Page | 2019-02-24
user | time statics and license statics | 08:51 I think the license statistics and time statistics are calling the same api and the values also the same, please check. | Completed
user |  | Even the individual filters are also the same issue, plese check and test from your end and then upload, now i am not checking the remaining time statistics part (monthly, weekly, this week). | Completed
user |  | 08:56 The years filter are changing like the same for both, please check. | Completed
user |  | 2019-02-25
user | all reports | Product names on top of the charts are mis matching, please cross verfy for all charts and reports for all users also, please check. | Completed | If still exists , please add a sheet and attach a screen shot
user | dasbhoar live chart | 03:34 For live chart the username sennding is different from actual user login. please check. | Completed
2019-02-26
department manager | recent reports | 11:52 Department manager - recent reports different charts not displaying only single format charts are displaying, please check. | Completed
department manager | reports | 1:08 In the first chart The year selected is different and the values displaying is different, please check. | Completed
department manager |  | 1:22 The year value is taking for all reports irrespective of chart product name report name. year 2016, 2019 does not exist for MSC and altair but it is taking :the year values of LSDYAN after click. | Completed
department manager |  | 1:31 For all charts individual filters the resize icon position is misplaced. check for all charts. | Completed
department manager |  | 2:44 When we click on years radio buttons, the current chart is not displaying but always line chart is displaying, please pass the current selected chart name.
department manager |  | 3:02 The Issues that were there for admin, are also present in dept manager report, please test from your end before uploading to server and also check for user also, i am testing for user. | Completed
department manager |  | 3:19 In all reports, after checking charts in individual filter when i come back to overall filters then the charts are not displaing properly, it shows trace 0, please check. | Completed
department manager |  | 3:26 The first chart is yearly chart and second chart is monthly chart. But because of the monthly polar chart, the yearly polar chart is also changing, please check. | Completed
department manager |  | 3:31 x axis title and years radio button overlapping. | Completed
department manager |  | 3:35 Please check the year radio buttons, pie chart, and polar chart that is linked to other reports polar chart and also the chart type upon clickiing radio buttons, | Completed | Chart type upon clicking radio buttons : It’s a duplicateof issue no 121.
department manager |  | 3:41 If in one chart if it does not receive any data and when we check other reports charts then even those reports also it is not receiving data and shows blank for all charts, please check this video. | Completed
department manager |  | 3:48 Monthly is not displaying any data but data is recived and for polar chart - if i click on monthly report - polar chart and then again click on yearly report - polar chart , Then it is displaying monthly polar chart in place of yealry polar chart. | Completed
department manager |  | 4:28 Same as above issue, The charts of monthly report are displaying in yearly report chart after clicking. | Completed
All users | favourites | loader for favourites section becuase currently it looks like no data found. | Completed
All users |  | Horizontal bar charts and bubble charts are not properly displaying. | Completed
All users |  | 2:41 resize functionalinty not working properly for admin, dept, user, and also please display whether it is time statics or license statistics below the product name and report name on the charts. | Completed | Could you update where to add time / license statistics content, There is not enough space to add full text , i.e license / time statistics
All users |  | 2:44 and also if there are any filter_user, filter_year, filter_department, values in response please display those also.
All users |  | 2:56 There are some changes in weekly report, please check. The API are different as per me. and also the years radio buttons and text overlapping. | Completed | Overallaping issue fixed , can you please update me API name
All users |  | 3:03 Both license statistics an time statistics are inter linked, The same is for admin and user also, please check. | Completed
All users |  | 3:10 Time statistics and license statistics are linked for all reports for all users, please cross verify before uploading to server. | Completed
All users |  | 3:35 The horizontal scroll bar is implemented, because there will be so many features, if it increases then auto horizontal scroll bar should come. | Completed
All users |  | 3:43 Please use different colours | Completed | Color will be mapped to legend, not for bar . For example if there are 4 different year for bar chart , the 4 different legends and 4 different color
All users |  | 3:47 I clicked on individual filters and then selected time sttistics, the charts itself opens for individual filters and with some radio buttons selected, because i have open individual filters of license statistics of same product and report. please check. | Completed
All users |  | 3:55 For Time statistics x-label is different from what currently exists. | Completed
All users |  | 4:03 There are inter linking between many charts, i am unable to understand which is linked to which chart, please cross verify before new deployment.
user | favourites | 4:16 When favourites is empty, the loader is still loading indefinitely. | Completed
user |  | please change the color of the text message to different color, when favourites is added.. | Completed
user |  | 4:24 years are repeating in the charts. and i think two different charts are displayed in one graph. | Completed
user | profile | email field should be automatically filled up. | Completed
user | reports | 4:35 Many same issues are existing for user also, please cross check. | Completed
user |  | 4:41 In This week report, the report names are changing and also the pie chart and some charts are not displaying, please check. | Completed
user |  | 4:44 Time statistics are also interlinked, please cross verif for remaining reports for license and time statistics | Completed
user
user | fotgot password | for the first time when i click on forgot password, the otp is empty, and i have reset the password. but when i click on forgot password again and go to otp page, then the otp is already filled with old otp. but it has be cleared and should be empty | Completed
all users | weekly report | year filter is not displaying for weekly, so unable to understand for which year this months represent. | Completed
all users | Side menu panel | when i select this week report in time statistics, initially this week report in time statisics is highlighted but when i try filtering in the chart then the this week report in license statistics is getting highlighted. and also when i select day shift filter still the day session wise is showing.
all users | This week report | In This week report, the filters day session, shift sessions, are displayed only for first time, but when i change to different chart types and coming again back to line chart also, they are not displaying. please check.
all users | All reports | Pie charts and bubble charts, scatter charts are not displaying for many charts, please cross check before uploading, and if any changes required from backend, please inform. | Completed
all users |  | loader not displaying in favourites page for all users. | Completed
all users |  | polar chart is missing for weekly, this week report user filters. pie chart and box plot are not implemented. | Completed
all users |  | No year filters for weekly report in individual fiter. | Completed